## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | WEB DEVELOPMENT
INTERN NAME: | NIDHI KRISHNA PEDNEKAR
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 2024-06-30
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | CourseConnect
PROJECT ID
INTERN NAME | Nidhi Krishna Pednekar
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
CourseConnect is a transformative platform designed to streamline access to IT and management colleges. Implemented with rigorous testing strategies including unit, integration, and system testing, it adheres to agile methodologies for iterative development and continuous improvement. This approach ensures CourseConnect remains adaptable and user-centric, enhancing the discovery of courses and institutions for students while maintaining high standards of reliability and functionality.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
CourseConnect's testing focuses on key features such as location-based college search, real-time result display, and user authentication. It ensures responsive design across devices and data integrity in the MySQL database, with optimizations for frontend and backend performance.
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
CourseConnect's testing excludes advanced features like social media integration, user-generated content moderation, and complex analytics. Non-functional aspects such as performance under extreme loads beyond current user projections and compatibility with outdated browsers are also not tested.
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
. Simplify college and course discovery for users through an intuitive platform. . Enhance user accessibility to college information and course details. . Improve search functionality for efficient browsing of colleges and courses. . Provide a seamless user experience without extensive testing considerations
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
Nidhi Krishna Pednekar-Project Manager and Developer Nidhi Krishna Pednekar-Designer Nidhi Krishna Pednekar-Backend Developer Nidhi Krishna Pednekar-Database Administrator Nidhi Krishna Pednekar-Technical Writer Nidhi Krishna Pednekar-System Architect
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
• WaterFall
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
For CourseConnect, the testing strategy encompasses multiple levels to ensure robustness and reliability. Unit testing verifies individual components such as frontend UI elements and backend APIs. Integration testing validates interactions and data flow between these components. System testing evaluates the entire system's functionality and performance, while user acceptance testing ensures alignment with business requirements and user expectations. Regression testing safeguards against unintended impacts from changes. Together, these levels ensure thorough validation across CourseConnect's development lifecycle, aiming for a seamless and user-friendly experience.
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
Bug triage in CourseConnect involves a systematic approach to managing reported issues. Each bug is assessed based on severity, impact on functionality, and user experience. Critical bugs affecting core functionalities are prioritized for immediate resolution to maintain system integrity and usability. Bugs with lower severity or impact are scheduled based on development resources and impact on user experience. The triage process ensures that all reported issues are addressed efficiently, aiming to enhance the overall reliability and performance of CourseConnect.
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
Ensure all functional requirements are tested thoroughly. Validate non-functional requirements such as performance, usability, and security. Conduct regression testing to prevent new issues in existing features. Test across different browsers for compatibility. Verify data integrity and accuracy.
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
Here are the sample deliverables • Test Plan • Test Cases • Test Data • Bug Reports • Test Scripts • Test Summary Report
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
Postman Selenium Jest JIRA MySQL Workbench Chrome Developer Tools
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Processor: Intel Core i5 or equivalent Memory (RAM): 8 GB Storage: Minimum 256 GB SSD Display: 15-inch monitor Network: High-speed internet connection with at least 100 Mbps bandwidth
ADDITIONAL COMMENTS
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Functional Testing | Verify all interactive functionalities on the frontend (search, display results, navigation) | 2024-06-29 | 2024-06-30 | Nidhi Krishna Pednekar | PASSED
Performance Testing | Measure application response times under varying loads | 2024-06-29 | 2024-06-30 | Nidhi Krishna Pednekar | PASSED
Security Testing | Conduct penetration testing to identify vulnerabilities in login and data handling | 2024-06-29 | 2024-06-30 | Nidhi Krishna Pednekar | PASSED
Compatibility Testing | Test application compatibility across different browsers (Chrome, Firefox, Safari) | 2024-06-29 | 2024-06-30 | Nidhi Krishna Pednekar | PASSED
Database Testing | Validate data integrity and performance of SQL queries for college and course data | 2024-06-29 | 2024-06-30 | Nidhi Krishna Pednekar | PASSED
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.