## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | WEB DEVELOPMENT
INTERN NAME: | NIDHI KRISHNA PEDNEKAR
PROJECT NAME: | COURSECONNECT
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2024-06-30
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME |  |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER
PROJECT SPONSOR
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2024-06-01 | Inaccurate requirement gathering | Requirements Management | YES | Conduct thorough initial stakeholder interviews and requirement workshops. | Scheduled regular requirement reviews with stakeholders. | Nidhi Krishna Pednekar | SOLVED
2 | 2024-06-09 | Unexpected technical issues | Technical Management | NO | Implement more robust testing protocols during development. | Increased focus on automated testing and QA checks | Nidhi Krishna Pednekar | SOLVED
3 | 2024-06-19 | Delay in integrating search functionality | Project Management | NO | Allocate more time for integration testing in the project schedule. | Implemented phased integration approach with iterative testing. | Nidhi Krishna Pednekar | SOLVED